## Slide 1
REGIONAL CYBER CENTER — KOREA
OPERATION CYBER STORM
CONSTRUCTION TIMELINE & DELIVERABLE TRACKER
29
DAYS TO COMPLETE
9
ACTIVE CONTAINERS
2
EVENT TRACKS
APR 6
COMPLETION DATE
PHASE 1: Foundation (Mar 8–15)
PHASE 2: Build (Mar 16–26)
PHASE 3: Integration (Mar 27–Apr 2)
PHASE 4: Rehearsal & Launch (Apr 3–6)
UNCLASSIFIED // FOR OFFICIAL USE ONLY | RESTRICTED — DO NOT DISTRIBUTE TO PARTICIPANTS

## Slide 2
MASTER GANTT — OPERATION CYBER STORM
Mar 8 — Apr 6 | 29 days
WK 1
Mar 8–15
WK 2
Mar 16–22
WK 3
Mar 23–29
WK 4
Mar 30–Apr 6
PHASE 1: Foundation
Event design & challenge spec
Docker architecture finalized
CTFd cloud instance provisioned
GitHub repo created + guides published
Registration form live
PHASE 2: Build
Container 1 — Splunk + logs
Container 2 — nginx/PHP/SQLite
Container 3 — nginx static (Recruit)
Container 4 — Flask cookie
Container 5 — Ubuntu SSH
Container 6+7 — Kali shared boxes
Container 8 — Ubuntu privesc
Container 9 — nginx phishing
CTFd challenge entry + flags
Q-Block entry + validation
PHASE 3: Integration
End-to-end chain test (Stages 3→6)
Recruit track full walkthrough
Hint system configuration
Kali box tool verification
rockyou.txt passphrase verification
Participant comms + guide distro
PHASE 4: Rehearsal & Launch
Full instructor walkthrough
AAR script review
Operator event — LIVE
Recruit 48hr window OPEN
ALL DELIVERABLES DUE — APR 6
TODAY
APR 6

## Slide 3
PHASE 1: FOUNDATION
Mar 8–15 | 8 days
PLANNING & DESIGN
Mar 8
Event spec + challenge design finalized
Mar 8
Docker container architecture confirmed (9 active + 1 reserve)
Mar 9
Confirm Mattermost/comms channel choice for event support
Mar 10
CTFd cloud instance provisioned and tested
Mar 10
CTFd categories created (Recruit + Operator)
Mar 11
Registration form built and live (Google/MS Forms)
Mar 11
QR codes generated for guides + registration form
Mar 12
GitHub repo created — student guides published as PDFs
Mar 13
Advertising flyer finalized with QR codes embedded
Mar 14
Flyer distributed to target audience
Mar 15
Phase 1 review — all planning artifacts complete
DOCUMENTS COMPLETED
✓ DONE
Student Guide — Recruit Division v3
✓ DONE
Student Guide — Operator Division v3
✓ DONE
Instructor Guide v3 (answer keys + container specs)
✓ DONE
Executive Summary v3
✓ DONE
CONOP Slide
✓ DONE
Advertising Flyer v4
Mar 15
Export all guides to PDF for GitHub hosting
Mar 15
Question banks reviewed and locked (Recruit + Operator)
Mar 15
Flag list finalized and version-controlled

## Slide 4
PHASE 2: BUILD — CONTAINERS & CTFd
Mar 16–26 | 11 days
1
Splunk Free
Mar 16–20
Operator
Pre-load 500MB synthetic logs; confirm C2 domain in DNS index; test SPL query resolution
2
nginx + PHP/SQLite
Mar 16–22
Operator
SQLi login, admin.php with hash display, /secret/ with ops_briefing.jpg + shadow.bak, generate SHA-512 hash for P@ssw0rd123
3
nginx static
Mar 16–19
Recruit
Stage 1 HTML page with hidden comment and robots.txt disallowed path containing flag
4
Flask cookie
Mar 18–21
Recruit
Stage 4 — role=user cookie portal, admin panel with flag revealed on role=admin
5
Ubuntu SSH
Mar 18–21
Recruit
Pre-load access.log with anomalous entry; plant hidden dot-file backdoor for Stage 6
6+7
Kali Linux (shared ×2)
Mar 21–25
Operator
Install full tool suite; confirm rockyou.txt present; isolate home dirs per user; test concurrent SSH
8
Ubuntu privesc
Mar 22–25
Operator
Add sudoers rule for find; set SUID on python3; create ctfuser + root; write flag to /root/flag.txt
9
nginx phishing inbox
Mar 22–25
Recruit
Static HTML mock webmail; raw headers toggle with FLAG in X-Mailer-ID; Reply-To mismatch for teaching
—
CTFd Challenges + Flags
Mar 24–26
Both
Enter all stage challenges; configure all flags; enter all Q-Block questions; set point values and hint tiers

## Slide 5
PHASE 3: INTEGRATION & HARDENING
Mar 27 – Apr 2 | 7 days
Mar 27
CRITICAL
Tech Lead
End-to-end Stage 3→4→5→6 chain test
SQLi → admin panel → gobuster /secret/ → download shadow.bak → john crack → steghide passphrase → extract file → SSH Container 8 → privesc → /root/flag.txt
Mar 27
CRITICAL
Tech Lead
Verify P@ssw0rd123 in rockyou.txt
grep -c 'P@ssw0rd123' /usr/share/wordlists/rockyou.txt — must return 1 on both Kali boxes
Mar 28
CRITICAL
Recruit Lead
Full Recruit track walkthrough
Complete all 7 stages + all 5 Q-Blocks as a participant would, from a clean Kali VM
Mar 28
CRITICAL
Operator Lead
Full Operator track walkthrough
Complete all 6 stages + all 5 Q-Blocks, using shared Kali box. Time each stage.
Mar 29
HIGH
Tech Lead
CTFd hint system configured
All hint tiers entered per Instructor Guide Section 4. Test hint purchase on test account.
Mar 29
HIGH
Tech Lead
CTFd flag validation sweep
Submit every flag from the answer key on a test account. Verify all 13 flags accepted correctly.
Mar 30
HIGH
Tech Lead
Kali box concurrent load test
Open 10 simultaneous SSH sessions to each Kali box. Run nmap + gobuster + john concurrently. Confirm no degradation.
Mar 30
HIGH
Recruit Lead
Container 9 browser test
Test phishing inbox in Firefox, Chrome, and mobile browser. Confirm raw headers toggle works and X-Mailer-ID flag is visible.
Mar 31
HIGH
Event Director
Participant communications sent
Email to all registered participants with event dates, CTFd URL, Kali requirement reminder, and guide download QR codes
Apr 1
MEDIUM
Event Director
Helpdesk channel established
Create and test the event support channel. Brief all instructors on escalation paths for common issues (see Instructor Guide Section 5.3).
Apr 2
MEDIUM
Tech Lead
Reserve container prepped
Container 10 (reserve) pre-built and ready to swap. Document which active container it is cloned from.
Apr 2
GATE
All
PHASE 3 GO/NO-GO REVIEW
All containers passing, all flags validated, both track walkthroughs complete. If any CRITICAL item open: delay launch.

## Slide 6
PHASE 4: REHEARSAL & LAUNCH
Apr 3–6 | 4 days
EVENT RUN SCHEDULE
Apr 3
Instructor dry run — full Operator track timed walkthrough with second instructor present
Apr 3
AAR script reviewed by all instructors
Apr 4
CTFd scoreboard cleared and reset for live event
Apr 4
Container health check — all 9 active containers confirmed up
Apr 5
Operator event check-in — distribute Kali box SSH credentials to participants
Apr 5
OPERATOR DIVISION LIVE EVENT — 3-4 hour window
Apr 5
Operator AAR conducted immediately post-event (20-30 min)
Apr 5
RECRUIT DIVISION 48-HOUR WINDOW OPENS
Apr 6
ALL DELIVERABLES COMPLETE — APR 6 DEADLINE
Apr 7
Recruit 48-hour window closes (if opened Apr 5)
Apr 7
Recruit async AAR walkthrough video recorded and published
COMPLETE DELIVERABLES LIST
DOCS
☐ Student Guide — Recruit Division v3
DOCS
☐ Student Guide — Operator Division v3
DOCS
☐ Instructor Guide v3 (full answer keys)
DOCS
☐ Executive Summary v3
DOCS
☐ CONOP Slide
DOCS
☐ Advertising Flyer (QR codes live)
DOCS
☐ Question Banks — Recruit (docx + xlsx)
DOCS
☐ Question Banks — Operator (docx + xlsx)
INFRA
☐ CTFd cloud instance — both tracks configured
INFRA
☐ Containers 1-9 built, tested, running
INFRA
☐ CTFd flags + Q-Blocks entered and validated
INFRA
☐ Hint system configured (Instructor Guide §4)
INFRA
☐ Kali boxes — tools verified, rockyou.txt confirmed
COMMS
☐ Registration form live + promoted
COMMS
☐ GitHub repo — PDF guides published
COMMS
☐ Participant comms + guide distribution sent
COMMS
☐ Helpdesk channel active
EVENT
☐ Operator Division live event executed
EVENT
☐ Operator AAR completed
EVENT
☐ Recruit Division 48-hr window opened

## Slide 7
CONTAINER ALLOCATION — FINAL (9 ACTIVE + 1 RESERVE)
#
Container
Track
Stage(s)
Key Build Task
Target Date
1
Splunk Free
Operator
Stage 1
Pre-load 500MB synthetic logs; C2 domain in DNS index
Mar 20
2
nginx + PHP/SQLite
Operator
Stages 3+4
SQLi vuln app + admin panel hash display + /secret/ with shadow.bak
Mar 22
3
nginx static
Recruit
Stage 1
Hidden HTML comment + robots.txt disallowed path
Mar 19
4
Flask
Recruit
Stage 4
Cookie portal — role=user/admin with flag on admin panel
Mar 21
5
Ubuntu SSH
Recruit
Stages 5+6
Pre-loaded access.log + planted hidden dot-file backdoor
Mar 21
6+7
Kali Linux (shared ×2)
Operator
All stages
Full tool suite; isolated home dirs; rockyou.txt verified; concurrent SSH tested
Mar 25
8
Ubuntu privesc
Operator
Stage 6
sudoers find rule + SUID python3 + ctfuser account + /root/flag.txt
Mar 25
9
nginx phishing
Recruit
Stage 7
Static HTML mock webmail; raw headers toggle; FLAG in X-Mailer-ID
Mar 25
10
RESERVE
Both
—
Emergency spare — clone whichever container needs backup on event day
Apr 4